## Register
Etyme — defect register
Eighteen broken loops found by tracing every designed flow. Severity drives order. Fill in Owner, Status and Target date; leave the rest as the record of what was found.
Legend — edit only the three yellow columns (J, K, L). Severity: Fatal changes what you build · Serious will hurt in month three · Fixable can wait · Known limit has no fix.
ID | Area | Flow | Severity | Defect type | The defect | Consequence if unfixed | Solution | Effort | Owner | Status | Target date
D-01 | Sign-up | Sign-up to first value | Fatal | Promise with no mechanism | The homepage promises a scored bench within the hour. Behind the form there is no reply owner, no route for CVs to arrive, no parsing step and no requirement to score against. | A vendor signs up, nothing happens, and they never come back. Every other loop in the product is downstream of this one. | Keep the first ten vendors manual and make the manual fast. Add a 'paste a requirement you are working on now' field to the form. Return the scored shortlist as a link or PDF with no account required — the login comes after the value, never before. | S |  | Open | Before code
D-02 | Sign-up | Contacting consultants | Fatal | Missing flow + legal | There is no consultant sign-up at all. They enter because a vendor uploaded a file about them, and the design then starts texting them. Nobody opted in. | In the US, texting individuals without prior express consent carries statutory damages per message. Vendor assurance is not clearly a defence. | First message is an opt-in, not a ping: it names the vendor, says why they are hearing from you, and STOP works from message one. Freshness pings start only after a yes. Store consent per person with timestamp and source. Vendor confirms the relationship at upload. Legal review before the first send. | M |  | Open | Before code
D-03 | Business | Agent share rising 30% to 88% | Fatal | Hope, not a mechanism | Adding eval cases measures the problem but never fixes it. Nothing in the design changes a prompt, a tool or the routing, and no trigger, owner or schedule says who would. | The margin curve carrying the whole business case never happens. Year four looks like year one at 45% instead of 84%. | Make it a named weekly loop. Every Friday, one person takes the top failure cause by volume, makes one change, re-runs a frozen eval set, and keeps or reverts on first-pass yield. One hour, one person, written down. | S |  | Open | Before code
D-04 | Cross-cutting | Outcome feeding the learning loops | Fatal | Loop never closes | Clients often never say why a candidate was rejected. The feedback arrow that every learning loop depends on arrives less than half the time. | Triage never learns which requirements you win, vendor scores cannot be computed, and the rate benchmark starves. | Treat silence as a label rather than missing data. Infer outcomes from observable signals: not viewed in 14 days, requirement closed with nobody hired, candidate placed elsewhere. Build the schema for inferred outcomes now — retrofitting it later is a rewrite. | M |  | Open | Before code
D-05 | Business | Five good submissions per day | Fatal | Cannot be diagnosed | One number with no decomposition. Five different causes produce the same stalled figure and each needs an opposite fix. | In month three, exactly when it matters, you cannot tell whether the problem is triage, the bench, consent, the check or requirement volume. You guess. | Replace the single number with a six-stage funnel: requirements arrived, passed triage, had a bench match, consent given, passed the check, sent. The drop between stages names the cause. | S |  | Open | Before code
D-06 | Sign-up | The first scored bench | Serious | Missing precondition | Scoring requires a live requirement. A brand-new vendor has none in the system, so the demonstration has no fuel. | The moment that sells the product cannot be produced for a new customer. | Collect a real requirement on the sign-up form. They have one open in another tab; it costs them ten seconds and it is exactly what the scoring needs. | S |  | Open | Before code
D-07 | Sign-up | An inbound lead arrives | Serious | Dead end | A form submission has no owner, no reply-time target and no second attempt. | Leads die quietly at 9pm on a Friday, and a dead lead teaches you nothing about who to approach next. | One named person, a two-hour reply target during working hours, two follow-up attempts, then closed with a reason from a short list. The reason is the loop. | S |  | Open | Phase 1
D-08 | Business | Prime vendor and platform at once | Serious | Trust boundary | You supply your own consultants while also running the platform. Standard master-vendor model, but sub-vendors will suspect front-running unless the rules are explicit. | Sub-vendors never complain — they quietly stop sending their good people. Supply then caps at the size of your own bench, which is the thing sub-vendors exist to uncap. | Label your own submissions in the client's inbox and put the arrangement in the contract. Then run the six supplier rules on the 'Supplier rules' tab: same clock, same score, same feedback, ranked on results, published share, categories you sit out. | M |  | Open | Phase 1
D-09 | Business | Free until it works | Serious | Undefined boundaries | The trial has no defined start date and no defined end. Both sides will remember it differently. | The disagreement surfaces at exactly the moment you are asking for money. | Write it at sign-up: the clock starts on the first uploaded bench, ends at five good submissions a day or ninety days, whichever comes first, and both sides read the same dashboard throughout. | S |  | Open | Phase 1
D-10 | Vendor | Escalation after three failed checks | Serious | Dead end | A person fixes the submission by hand and nothing about the cause is recorded. | The identical failure returns next week, and the week after. The human becomes a permanent absorber of the same error. | Every escalation closes with a cause chosen from a short list. Causes aggregate. When one reaches ten occurrences it becomes a work item against the agent — which is how the weekly improvement loop gets fed automatically. | M |  | Open | Phase 2
D-11 | Vendor | Consultant freshness | Serious | Collects rubbish | Two pings with no reply marks someone unconfirmed, and then nothing. There is no archive rule and no path back to confirmed. | Within a year a large share of the bench is people who left the market, still counted in the idle-bench-days figure the vendor dashboard leads with. The hero metric corrupts itself. | Unconfirmed for 30 days raises one call task for a recruiter. Still nothing at 60 days, archive automatically and drop them from every count. One click restores them if they resurface. | S |  | Open | Phase 2
D-12 | Client | Requirement changes mid-flight | Serious | Missing state transition | Nothing handles a rate moving, a location changing or a role being cancelled after submissions have been scored. | Twenty scored submissions silently become wrong, and cancelled requirements keep burning compute downstream. | Version the requirement. Stamp every score with the version it was scored against. On change, re-score what is in flight and flag stale shortlists. On cancel, hard-stop everything downstream immediately. | M |  | Open | Phase 2
D-13 | Client | Requirement quality check | Serious | Routed to the wrong person | 'Rate below market' is shown to whoever typed the requirement, usually a coordinator with no authority over pay. | They cannot act, so they override. Within a month overriding is reflexive and the check is theatre. | Route each problem to whoever can act on it — rate goes to the hiring manager with the market data attached. Track the override rate; above half, the check is failing rather than the user. | M |  | Open | Phase 2
D-14 | Client | Human sample review | Serious | No sampling discipline | 'Ten a week' with no rule for which ten. Left to a person they review the easy ones; left to 'most recent' the rare failures are never seen. | The agreement rate looks excellent and means nothing, which is worse than having no check at all. | Assign the sample, never let it be chosen. Stratify it: some random, some from the 70-80 score band where errors cluster, some shortlisted, and every case where the rules and the model disagreed. | S |  | Open | Phase 1
D-15 | Vendor | Consent — the NO branch | Fixable | Dead end | The consent text asks yes or no. The design only says what happens on yes. | A no leaves the submission in limbo and throws away the most valuable reply available — 'someone already put me forward there'. | No cancels the submission, notifies the recruiter, and asks one follow-up: already submitted, rate too low, or not interested. That third answer is free deduplication and free market data. | S |  | Open | Phase 2
D-16 | Client | Deduplication | Fixable | Dead end | A person judges 'not the same person' in the check queue. The verdict corrects that one record and vanishes. | The rule that made the mistake is unchanged, so it makes the same false merge again. | The human verdict becomes training data rather than a one-off correction. Feed disagreements back into the matching thresholds on a monthly review. | M |  | Open | Phase 3
D-17 | Client | Rate benchmark | Fixable | Circular reasoning | Market rates are built from your own submissions, then used to tell clients their rate is below market. | Early on your bench is the entire sample, so an expensive bench makes every client look underpriced. | Do not use the benchmark below a minimum sample size per skill and city, and show the sample size beside every figure. Sanity-check the first year against published survey data. | S |  | Open | Phase 3
D-18 | Vendor | Submission check | Known limit | Check cannot verify truth | The check confirms the CV asserts seven years of a skill. It cannot confirm the seven years happened. A well-written fabrication passes cleanly. | If sold as fraud detection, the first fabricated CV that reaches a client ends the relationship. | No fix exists and pretending otherwise is worse than admitting it. The check catches sloppiness; interviews catch lying. Never describe it as fraud detection in any sales conversation or on the site. | - |  | Open | Ongoing
Summary |  |  | Counts are live formulas over the table above — they update as you change Status.
Fatal
Serious
Fixable
Known limit
TOTAL
Open
Note on F5: Every entry here was found by tracing the designed flows, not by testing a running system. Nothing has been built yet, so these are design defects rather than observed bugs.

## Fix first
Fix these five before any code
The other thirteen can be fixed as you go. These five change what gets built — and the first two change what happens this week.
# | What to do | Defects it closes | Why it cannot wait | Done looks like
1 | Get the SMS consent question in front of a lawyer | D-02 | Before a single message goes out — not before launch, before the first message. Everything else here is a design decision you can revise. This one has statutory damages attached and no amount of good intent undoes a send. | Written confirmation of the opt-in wording and the consent record you must keep.
2 | Make the first hour real, by hand | D-01, D-06, D-07 | Add the requirement field to the sign-up form, name one person to reply within two hours, and send the scored shortlist back without asking anyone to create an account. | Ten vendors onboarded manually, each with a scored shortlist delivered inside an hour.
3 | Put a name and a Friday on the improvement loop | D-03 | One person, one hour a week, one change, measured against a frozen eval set, kept or reverted on the number. | A dated log of changes with first-pass yield before and after each one.
4 | Assume outcomes will not arrive, and infer them | D-04 | Treat silence as a label. Design the inferred-outcome signals into the schema now rather than retrofitting them. | Outcome table accepts inferred as well as reported results, with the source recorded.
5 | Build the funnel, not the number | D-05 | Six counters instead of one, on data you are already storing. | The vendor dashboard shows the six-stage funnel, not a single submissions-per-day figure.

## Supplier rules
Running as prime vendor without losing your sub-vendors
Policy, not defects — these close D-08. Supplying your own consultants while running the platform is the master vendor model and is entirely normal. The risk is not the client objecting, it is sub-vendors quietly leaving.
Rule | What it means in the product | Why they will not stay without it
Same clock | Every supplier, including your own bench, is notified in the same second. No pre-release, ever. | A thirty-minute head start is invisible to you and obvious to them within a month.
Same score | Your consultants run the identical check and scoring, with the same evidence shown. | You already show the working on every match. That is your proof of fairness, and no other platform can offer it.
Same feedback | Every supplier sees why they lost and where they ranked, not only the winner. | Without it they cannot improve, so they cannot win, so they leave. Same dead end as half the defects in this register.
Ranked on results | Distribution order comes from placement rate, never from ownership. | The moment the order is 'us first', the vendor scorecard is decoration.
Published share | Show suppliers how often your own bench wins, per category, openly. | They will work it out anyway. Publishing it is either a recruitment pitch or an early warning.
Categories you sit out | Name skill areas where your own bench does not bid at all. | The cheapest trust you will ever buy, since you cannot cover every skill anyway.
The test of whether you mean it
On your own consultant you bill $85, pay $60 and keep $25. On a sub-vendor placement you might keep $10 — but with no bench to carry, no idle days and no ceiling on coverage. The blended business beats either alone, which means you should genuinely want sub-vendors to win sometimes. If that sentence sits badly, the model will not hold, because every rule above costs you a placement you could have taken.